## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | iFace
PROJECT MANAGER | Nurul Aina Zafirah Binti Muhamad Sani (B031910143)
GROUP NAME | NURAFIQAH BINTI KHOSNI (B031910083) | MUHAMMAD AMIRUL SYAFIQ BIN ZULKEFLI (B031910016) | WAN ADDINI AISYAH BINTI WAN ISMAIL (B031901404)
COMPANY NAME | ForA
DATE | 2021-10-11 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | T | F | M | T | W | T | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | Project Charter | Aina | 2021-10-04 | 2021-10-07 | 3 | 100%
1.1.1 | Project Charter Revisions | Amirul | 2021-10-08 | 2021-10-09 | 1 | 100%
1.2 | Research | Afiqah, Amirul | 2021-10-10 | 2021-10-15 | 5 | 100%
1.3 | Projections | Addini, Aina | 2021-10-10 | 2021-10-15 | 5 | 100%
1.4 | Stakeholders | Addini | 2021-10-16 | 2021-10-21 | 5 | 100%
1.5 | Guidelines | Amirul | 2021-10-16 | 2021-10-21 | 5 | 100%
1.6 | Project Initiation | Afiqah, Aina | 2021-10-22 | 2021-10-22 | 0 | 100%
2 | Project Definition & Planning
2.1 | Collect Requirement | Addini | 2021-10-23 | 2021-11-02 | 10 | 100%
2.2 | Goal Setting | Addini | 2021-10-25 | 2021-10-28 | 3 | 100%
2.3 | Define Scope | Aina | 2021-10-23 | 2021-10-27 | 4 | 100%
2.4 | Create WBS | Amirul | 2021-10-28 | 2021-10-31 | 3 | 100%
2.5 | Verify Scope | Afiqah | 2021-11-01 | 2021-11-02 | 1 | 100%
2.6 | Control Scope | Amirul, Addini | 2021-11-03 | 2021-11-05 | 2 | 100%
2.7 | Budget (NPV) | Afiqah, Aina | 2021-11-05 | 2021-11-07 | 2 | 100%
2.8 | Communication Plan | Amirul | 2021-11-08 | 2021-11-10 | 2 | 0%
2.9 | Risk Management | Aina | 2021-11-11 | 2021-11-15 | 4 | 0%
3 | Project Launch & Execution
3.1 | Status & Tracking | Aina | 2021-11-15 | 2021-11-17 | 2 | 0%
3.2 | KPIs | Afiqah | 2021-11-18 | 2021-11-21 | 3 | 0%
3.2.1 | Monitoring | Aina | 2021-11-15 | 2021-12-11 | 26 | 0%
3.2.2 | Forecasts | Amirul | 2021-11-22 | 2021-11-23 | 1 | 0%
3.3 | Project Updates | Addini | 2021-11-24 | 2021-11-28 | 4 | 0%
3.3.1 | Chart Updates | Afiqah | 2021-11-29 | 2021-12-03 | 4 | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Addini | 2021-12-06 | 2021-12-08 | 2 | 0%
4.2 | Quality Deliverables | Aina | 2021-12-06 | 2021-12-08 | 2 | 0%
4.3 | Effort & Cost Tracking | Afiqah | 2021-12-09 | 2021-12-11 | 2 | 0%
4.4 | Project Performance | Amirul | 2021-12-09 | 2021-12-11 | 2 | 0%
Formulas:
DURATION = DAYS([DUE DATE],[START DATE])

## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE | [6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%