## TIME MANAGEME Gantt Chart BLANK
TIME MANAGEMENT GANTT CHART TEMPLATE
PROJECT TITLE | iFace
PROJECT MANAGER | Nurul Aina Zafirah Binti Muhamad Sani (B031910143)
GROUP NAME | NURAFIQAH BINTI KHOSNI (B031910083) | MUHAMMAD AMIRUL SYAFIQ BIN ZULKEFLI (B031910016) | WAN ADDINI AISYAH BINTI WAN ISMAIL (B031910404)
COMPANY NAME | ForA
GITHUB LINK | https://github.com/AinaZafirah/iFace
TASK NAME | START DATE | END DATE | DURATION (days)
1. Project Conception & Initiation | 2021-10-04 | 2021-10-22 | 19
1.1 Prepare Project Charter | 2021-10-04 | 2021-10-15 | 12
1.2 Identify Key Stakeholders | 2021-10-16 | 2021-10-21 | 6
1.3 Hold Project Kick-off Meeting | 2021-10-22 | 2021-10-22 | 1
2.0 Project Definition & Planning | 2021-10-23 | 2021-11-15 | 24
2.1 Plan scope management | 2021-10-23 | 2021-11-04 | 13
2.1.1 Collect Requirement | 2021-10-23 | 2021-11-02 | 11
2.1.1.1 Interview Stakeholder | 2021-10-23 | 2021-10-28 | 6
2.1.1.2 Focus Group | 2021-10-29 | 2021-11-02 | 5
2.1.2 Goal Setting | 2021-10-25 | 2021-10-28 | 4
2.1.3 Define Scope | 2021-11-03 | 2021-11-04 | 2
2.1.3.1 Analysis Product | 2021-11-03 | 2021-11-04 | 2
2.2 Plan Schedule Management | 2021-10-28 | 2021-10-31 | 4
2.2.1 Create WBS | 2021-10-28 | 2021-10-31 | 4
2.3 Cost Management | 2021-11-05 | 2021-11-07 | 3
2.3.1 Calculate NPV | 2021-11-05 | 2021-11-07 | 3
2.4 Quality Management | 2021-11-07 | 2021-11-08 | 2
2.4.1 Workshop Training | 2021-11-07 | 2021-11-08 | 2
2.5 Communication Management | 2021-11-08 | 2021-11-10 | 3
2.5.1 Communicate with Stakeholder | 2021-11-08 | 2021-11-09 | 2
2.5.2 Communicate with Development Team | 2021-11-09 | 2021-11-10 | 2
2.6 Risk Management | 2021-11-11 | 2021-11-15 | 5
2.6.1 Identify Risk | 2021-11-11 | 2021-11-15 | 5
3.0 Project Launch & Execution | 2021-11-16 | 2021-11-16 | 1
3.1 Acquire and Develop Project Team | 2021-11-16 | 2021-11-16 | 1
3.1.1 Assign Role | 2021-11-16 | 2021-11-16 | 1
3.2 Direct and Manage Project Work | 2021-11-17 | 2021-11-17 | 1
3.2.1 Start Developing Project | 2021-11-17 | 2021-11-17 | 1
3.3 Manage Communications | 2021-11-17 | 2021-11-17 | 1
3.3.1 Project Meeting | 2021-11-17 | 2021-11-17 | 1
3.4 Manage Stakeholder Engagement | 2021-11-17 | 2021-11-17 | 1
3.4.1 Get Stakeholder Verification | 2021-11-17 | 2021-11-17 | 1
3.5 Project Updates | 2021-11-17 | 2021-11-17 | 1
4.0 Monitoring & Controlling | 2021-10-28 | 2021-12-30 | 64
4.1 Monitor and Control Project Work | 2021-11-17 | 2021-12-28 | 42
4.2 Control Scope | 2021-11-17 | 2021-11-21 | 5
4.2.1 Validate Scope | 2021-11-17 | 2021-11-21 | 5
4.3 Control Schedule | 2021-10-28 | 2021-12-28 | 62
4.4 Control Cost | 2021-11-21 | 2021-11-29 | 9
4.4.1 Create a Baseline | 2021-11-21 | 2021-11-23 | 3
4.4.2 Calculate a Variance | 2021-11-24 | 2021-11-25 | 2
4.4.3 Investigate Variance | 2021-11-26 | 2021-11-27 | 2
4.4.4 Take Action | 2021-11-27 | 2021-11-29 | 3
4.5 Control Quality | 2021-11-21 | 2021-12-28 | 38
4.5.1 Get Feedback from Stakeholder | 2021-11-21 | 2021-12-28 | 38
4.6. Control Communication | 2021-11-21 | 2021-11-26 | 6
4.7 Control Risk | 2021-12-01 | 2021-12-07 | 7
4.7.1 Identify New Risk | 2021-11-01 | 2021-11-03 | 3
4.7.2 Respond to Risk | 2021-11-04 | 2021-11-06 | 3
4.7.3 Evaluate Risk Response | 2021-11-06 | 2021-11-07 | 2
4.8 Work Performance Information | 2021-11-17 | 2021-11-18 | 2
4.9 Verify Project | 2021-12-28 | 2021-12-30 | 3
5.0 Closing | 2021-12-30 | 2022-01-05 | 7
5.1 Finalize the Project | 2021-12-30 | 2022-01-01 | 3
5.2 Prepare Project Report | 2022-01-01 | 2022-01-03 | 3
5.3 Prepare Project Presentation | 2022-01-01 | 2022-01-03 | 3
5.4 Present Project | 2022-01-04 | 2022-01-04 | 1
5.5 Leesons Learned | 2022-01-05 | 2022-01-05 | 1
MILESTONE 1:
04/10/2021
Brief Description
MILESTONE 2:
23/10/2021
Brief Description
MILESTONE 3:
16/11/2021
Brief Description
MILESTONE 5:
31/12/2022
Brief Description
MILESTONE 4:
28/10/2021
Brief Description
Right click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.